## Table 1
Construction/Repair Works of Civil,Electrical & Plumbing in School Budiling
A | Cost Estimate of GGMS Gulshan RehmanColony-Peshawar.
S/N | MRS-2022 Ref: | Activities | Unit | Quantity | Unit Rate | Total Cost
[5 empty] | PKR | PKR
1 | 04--13 | Dismantling brick work in lime or cement mortar | Cft | 640
2 | 04-19-c | Dismantling : Plain Cement Concrete 1:2:4 | Cft | 430
3 | NSI | Removing of Existing Damaged Doors and Windows | Each | 20
4 | 04-48-b | Removing of damaged Plaster in inside face of boundary wall (10 ft avg height) | Sft | 1050
5 | 06-05-f | Provide & lay topping of concrete 1:2:4, including surface finishing & dividing in panels : | Cft | 741
6 | 07-05-a-02 | Pacca brick work in ground floor Cement, sand mortar 1:3 | Cft | 183
7 | 25-38 | Providing and Fixing GI wire gauze 24 SWG, (12x12) meshes per sq.in., fixed to steel windows or doors etc, complete in all respects | Sft | 128
8 | 27--04 | Repairing & re-fixing of steel main gate i/c hold fast, welding complete in all respects 40) | Sft | 235
9 | 11-07-b | Cement plaster 1:2, upto 20' height 1/2" thick | Sft | 1414
10 | 25-44 | Supplying and Fixing 18SWG Steel Almirah, 12" max depth including box shelves, back, shelves, lock, spray paint complete | Sft | 80
11 | 25-45-a | Supplying and Fixing 18 SWG MS Sheet Door/ventilator with angle iron frame (1.5"x1.5"x1/8"), bolt, hinges, paint etc complete | Sft | 35
12 | 25-33-a | Providing and fixing terrace railing 2" i/d conduit pipe 16 SWG, welded with 5/8" x 5/8" square bar 2.75 ft. high fixed at 5" center to center, in RCC slab with suitable arrangement, complete in all respects as per site requirements and matching with the existing railing. | RFt | 55
13 | 12-57-b | Providing and fixing double leaf steel door with frame fully panelled with M.S sheet 16 gauge (1.59mm) painted with two coats of red oxide paint with brass fitting of approved make including cost of fabrication, iron lugs, cutting holes and making good the damages to walls. | Sft | 136
14 | 25-39-b-05 | Providing and Fixing steel windows 18 gauge with openable glazed panels With 22 SWG wire gauze : Glass pane 5mm | Sft | 192
15 | 25-53 | Providing, making and fixing of steel grill of MS pipe (2"x1") omamental design i/c cost of paiting complete. | Sft | 192
16 | 04-45-b | Scraping : Ordinary distemper, oil bound distemper or paint off wall | Sft | 25153
17 | 11-21-b-02 | Distempering Old surface : Two coats | Sft | 25153
18 | 13-25-a+13-25- b | Preparing surface & painting with snowcem / weathershield paint : First coat and Second coat | Sft | 5208
19 | 14-105 | Supply and fixing of Glass Pane 5mm Black colour best quality imported | Sft | 50
20 | 10-39-a | Glazed tile 1/4" thick dado jointed in white cement complete : White Plain tiles | Sft | 638
21 | 13-02-c-02 | Painting old surfaces : Doors / windows any type Each subsequent coat | Sft | 8817
22 | 14-160-b | Electric water coolers of 40 gallons capacity, including inlet and outlet connections, gate valve on inlet, electric connection upto power socket, and all other accessories for complete installation.with alteast one year Warranty. | Each | 2
23 | 14-161 | Triple water filter (10") including inlet and outlet connections, power supply, and all accessories for complete installation | Each | 2
24 | 28-19 | Making notice board 1/2" thick of c/s mortar 1:3 with 2"x1/2" beading | Sft | 24
25 | NSI | Supply and Fixing White Board with aluminum frames is a dry Erase Board makes,the surface resist scratching and earses easily without ghosting ,having size (10x4 feet and minimum 1" Thick) Good Quality as per approved Standrad and Incharge Engineer. | Each | 9
26 | NSI | Welding of Exisiting CGI sheet used as Parapet wall, properly fixed with nut bolts ,welded etc in brick wall as per instruction of Engineer Inchrage. | Nos | 40
27 | NSi | Painting Cartoons and Writing Proverbs on Walls, complete in all respect or as directed by Engineer | Each | 5
Total Cost-A
B |  | Electrification Works
S/N | MRS-2022 Ref: | Activities | Unit | Quantity | Unit Rate | Total Cost
[5 empty] | PKR | PKR
1 | 15-06-c | Supply/errection Electric wire 7/29 pvc insulated+sheaSupply and Erection single core PVC nsulated+sheathed copper conductor 250/440 V grade cable : 7/0.029thed copper wire , 250/440 V grade(Pak/FAST cables) | Rft | 350
2 | 04--49 | Dismantling light, fan and call bell point including casing, capping/strip open type complete | Points | 30
3 | 15-50 | Wiring of light/fan/call-bell point in 3/0.029" PVC insulated bare cable in PVC pipe recessed | Points | 35
4 | 26-01-c-05 | Supply and erection of AC energy efficient LED light/Bulbs (7-10 W) ,Philips,Skyled or Equal event with at least 1 year Warranty. | No | 35
5 | 26-01-c-07 | Supply and Erection of AC ENERGY EFFICIENT LED LIGHT BULBS (21-30 W)Philips,Skyled or Equalevent with atleast 1 year Warranty. | No | 12
6 | 26-01-l-01 | Supply and Erection of AC ENERGY EFFICIENT CEILING FANS 56 inch, 50 W (National ,Pak or equivalent | No | 24
7 | 15-127-m | Supply at site, installation, testing and commissioning of Fan Dimmer with switch/ MS, powder coated back box with all associated accessories, complete in all respects | No | 24
8 | 15-84 | Supply and fitting of capacitor 2.2 uf for ceiling fans or as per requirement. | No | 30
9 | 15-69-a | Supply and erection best quality exhaust fan complete with shutter and regulator 12" sweep | Each | 2
10 | 15-09-f | Supply and Erection MS sheet box of 16 SWG, 4"deep with 3/16" thick bakelite sheet top etc. complete : 12"x14" | Each | 10
11 | 15-25 | Supply and erection girder clamp hook, 5/8" dia for hanging ceiling fans | Each | 8
12 | 15-71-a | Supplying and erection single phase imported auto circuit breaker 6 AMP | Each | 10
13 | 15-71-d | Supplying and erection single phase imported auto circuit breaker 30 AMP | Each | 10
|  | Total Cost-B |  |  |  | -
C |  | Sanitary/Plumbing
S/N | MRS-2022 Ref: | Activities | Unit | Quantity | Unit Rate | Total Cost
[5 empty] | PKR | PKR
1 | 14-71-b | Providing and Fixing of polydex high pressure PPR (green including testing ect complete 20 mm(including all special etc) | Rft | 230
2 | 14-71-a | Providing and fixing of polydex high pressure (PPR) green including testingn etc complete 1 " dia (25 mm including all specials) etc | Rft | 250
3 | 14-55-e | Providing and Fixing GI pipe & including specials complete: 3/4" dia (light) | Rft | 100
4 | 24-18-a-02 | Providing, laying, cutting, jointing, testing and disinfecting 4" dia UPVC pipe class B laid in trenches from WC, floor trap to manhole/septic tank/soakage pit all as specified | Rft | 25
5 | 24-18-a-01 | Providing, laying, cutting, jointing, testing and disinfecting 3" dia UPVC pipe class B for vent pipe | Rft | 13
6 | 24-33-c | Supplying and fixing, cast iron manhole cover with frame, etc. (Heavey Type) of approved quality complete. 18" (450 mm) dia. | Each | 2
7 | 14-03-a | Providing and fitting glazed earthenware water closet (WC), squatter type (orisa pattern) combined with foot rest. complete in all respects : White | Each | 2
8 | 14-24-b | Providing and fixing chromium plated bib-cock heavy duty of approved quality, Steel Bib-cock 1/2" dia | Each | 12
9 | 24-18-b-01 | Providing and Fixing UPVC ventilation pipe 2” dia with specials & cowl complete, class-C pipe | Rft | 13
10 | 14-32-a | Providing and Fixing 'P' trap of approved quality including GI grating & PCC chamber 4" (100 mm) of cast iron (Best Quality) | Each | 1
11 | 14-01-a | Providing and Fixing glazed earthen ware WC European type including cost of seat & cover all required specials/accessories | Each | 1
12 | NSI | Providing and Fixing CP grab rail : 5' long, 1" dia fixed as per drawing | Each | 2
13 | 14-69-b-03 | S/F polyethyene water tank made from food grade FDA certified raw materials 3 layers UV stablized inert with water, anti fungus and anti bacterial and have a service life of more than 10 years: 500 gallons (vertical) | Each | 1
14 | 14-10-a | providing and fixing glazed earthen ware low down flushing cistern 3 gallons capacity including bracket set , copper connection, etc . Complete in all respect, White | Nos | 4
15 | 14-06-a | Providing and Fixing stainless steel sink with drain board size (120 x 60 cm) 48"x24", including set of brackets, waste pipe etc - (Best Quality) | Each | 1
16 | 14-14-a | Providing and fixing choricum plated soap dish complete. | Each | 1
17 | 14-104-b | Supply and Fixing of CP floor Truff Jalli with Grating 6"×6" complete | Each | 4
18 | 14-17-a | Providing and fixing best quality looking glass 5 mm thick neatly fitted on masonry wall etc. as per instruction of Engineer In-charge complete. Mirror 60 x 45 cm (24"x18") size | Each | 1
19 | 14-86 | Providing & fixing chromium plated double bib-cock with Muslim Shower of approved quality Complete is all respects. | Each | 1
20 | NSI | Supply and fixing of lasani wood almirah having size in (18"x42") fixed in wall as per instruction of Engineer incharge in MHM washroom. | Each | 1
21 | NSI | Providing and fixing best quality looking glass 5 mm thick neatly fitted on masonry wall etc. as per instruction of Engineer In-charge complete. Mirror (36"x18") size (for MHM Only) | Each | 1
22 | NSI | Provision & installation of visibility Board (2x2) Steel with printing and Logos (Design Approved by Engineer) | Each | 1
23 | NSI | Supply and Fixing 3" i/d GI Pipe (Light) 18 feet Long ,Fixed in wall with clamps and welded 12 Nos of Super asia Or EquaL;Tap complete with all respect,and As per Instruction of Engineer incharge. | Job | 1
Total cost-C
D |  | Water Supply Scheme (Bore)
S/N | MRS-2022 Ref: | Activities | Unit | Quantity | Unit Rate | Total Cost
[5 empty] | PKR | PKR
1 | 24-01-c | Mobilization of equipment for drilling of small bore upto 8" dia | Job | 1
2 | 24-02-a-05 | Drilling of Bore holes for tube well in all types of soil and soft rock except hard rock from ground level upto 328 ft depth (0m to 100m), including sinking, collection of 100 % corings and withdrawing of pipe, complete as per specifications.: Dia of Bore 8" (200 mm) i/specifications.: Dia of Bore 8" (200 mm) i/d | Rft | 180
3 | 24-12-b-01 | Providing and installing PVC blind pipe BSS Class "C" in Tube Well Bore Hole including Sockets and Solvents and jointing with strainer etc. complete : 6" Nominal Pipe Size (NPS) (150 mm) | Rft | 180
4 | 24-14 | Shrouding with graded pack gravel 3/8" (10 mm) to 1/8" (3 mm) around tubewell in bore hole complete as per specification:- | Rfy | 180
5 | NSI | Submersible Water pump with Motor: Supply and installation of single phase 1.5 hp (1.1kw) and required supply cable from inverter to water pump motor ,steel rope etc. complete with all aspects as per instruction of Engineer. (JDs Or Equivalent. | Each | 1
6 | 24-30-b-02 | providing, laying, cutting, jointing, testing and disinfecting High Density Polyethylene Pipe (HDPE) Din-8074/Din-8075/ISO-4427 in trenches, complete in all respects except excavation. (25mm dia) PN-10 | Rft | 170
7 | NSI | Supply and Fixing of Steel cover lockable for bore hole Protection having size 1x1 feet with lock and 16 gauge as per instruction of engineering Inchareg. | Job | 1
Total cost-D
Grand Total Cost in PKRS=
General Note/Specification:- i).Payment will be paid to vendor as per Actual work done on site.And Vendor will submit MB of All Work done on site on Completion. ii).Prior start of any Activities the materials sample must be approved from Engineer In charge and approved material will be used. iii). All Activities will be done As per Engineering Standards and Govt of KP Specifications. iv). Govt Approved brands will be used and strictly follow the instructions. V).If Any changes would require on site ,would be review and approve for Engineer In charge prior Execution. VI).The price includes all builders’ Works, making good and reinstatement including necessary materials and workmanship as well as removal of unwanted materials to dump sites and tronsputation cost, asper instruction of Engineer Inchrage. Vii.As per national policy “The children under the age of 18 years cannot be employed and not be involve at any stage of construction Activities. Viii)All HSE related precautionary measure should be followed by vendor on site and the cost of HSE should include in quoted rates. iX).Employer is obligated to provide PPS such as high vis vests, safety goggles and safety harnesses to construction site workers and the Cost should inculde in the items Qaouted Rates.